## table-a377c446-1927-4eee-9093-2
Repository & Project Foundations
Status | Task | Note
✅ | Repository cloned and folder hierarchy (src/, scripts/, docs/, …) exists | The structure shown in the README matches the planned layout .
✅ | README.md with project overview, installation, and usage instructions is present | Provides the high‑level description and data‑analysis plan .
✅ | data_config.json / data_config.template.json for portable data paths | Template ready; just edit the actual data_root.
✅ | Conda environment file epa_mh.yaml created | Enables reproducible environment .
✅ | Basic data‑access utilities (src/data_paths.py) are available | Functions such as get_instrument_path already implemented .
✅ | Python package skeleton (src/__init__.py) set up | Allows import src style imports.
✅ | Example scripts (example_data_access.py, co2 plot.py) present | Demonstrate how to read and plot raw data .
Data Ingestion & Pre‑Processing
Status | Task | Action
⬜ | Write a generic loader (load_data.py) that reads CSV/TXT files from the locations listed in Data Analysis.docx (CO₂, QuantAQ, DAQ, logs) and returns a pandas.DataFrame with a unified datetime index. | Use the paths in the DOCX (I:\EPA Shower\…) as reference .
⬜ | Validate raw files for duplicates, missing timestamps, and obvious outliers; log any problems. | Create a simple quality‑control report (e.g., qc_report.txt).
⬜ | Resample all series to a common frequency (e.g., 10 s) and interpolate where appropriate. | Choose pd.DataFrame.resample(&#39;10S&#39;).interpolate() or similar.
⬜ | Merge Aranet CO₂ files (Bedroom, Entry, Outside) into a single DataFrame with columns C_bedroom, C_entry, C_outside. | Follow the “CO2 Analysis” instructions .
⬜ | Merge QuantAQ indoor/outdoor particle files, compute the penetration factor P (C/C_outside one hour before shower). | Use the 0.7‑0.9 target range noted in the DOCX .
⬜ | Create derived flags (shower_on, shower_off, fan_off) from the log timestamps. | Parse Log - Shower and Log - CO2 Injection.
CO₂ Decay & Air‑Change Rate (λ)
Status | Task | Action
⬜ | Implement the numerical “purple” equation that solves for λ at each time step, allowing C_bedroom, C_entry, and C_outside to be time‑dependent. | Use the description in the DOCX .
⬜ | Run the solver from 10 min before the hour up to 2 h after the CO₂ injection ends; store λ for every step. | Include the 40‑44 min injection window and fan‑off at 45 min.
⬜ | Compute average λ and standard deviation over the 2‑hour post‑injection period. | Export to co2_lambda_summary.csv.
⬜ | Calculate λ via the three alternative concentration selections (C_average, C_outside, C_entry) to assess uncertainty. | Record all three sets for later comparison.
Particle‑Size Decay & Deposition (β)
Status | Task | Action
⬜ | For each particle‑size bin (0.35‑0.46 µm … 2.3‑3 µm), solve the particle‑decay “purple” equation using the λ from CO₂ analysis and the previously computed P. | Follow the procedure in the DOCX .
⬜ | Determine the deposition loss rate β_deposition by finding the value that drives the emission term E to zero (solve numerically for each time step). | Implement a root‑finding routine (e.g., scipy.optimize.brentq).
⬜ | Average β over the 2‑hour post‑shower window and report its standard deviation per bin. | Save to particle_deposition_summary.csv.
⬜ | Compute emission rates during the 10‑minute shower using the numerically solved λ and β values. | Output particle_emission_rates.csv.
Relative Humidity (RH) Analysis
Status | Task | Action
⬜ | Load RH data from all listed instruments (Aranet 1‑3, QuantAQ 1‑2, DAQ locations). | Use the instrument list from the DOCX .
⬜ | For each location, calculate: • Mean ± SD for the 30‑min pre‑shower window. • Mean ± SD for the 2‑h post‑shower window. • Min/Max difference for the post‑shower period. | Store results in rh_summary.csv.
⬜ | Generate time‑series plots of RH for each sensor (optional). | Use seaborn/matplotlib.
Temperature Analysis
Status | Task | Action
⬜ | Same locations as RH (Aranet, QuantAQ, DAQ). | Pull temperature columns from the merged DataFrames.
⬜ | Report: • Pre‑shower mean ± SD (30 min). • Post‑shower mean ± SD (2 h). • Min/Max difference for post‑shower period. | Save to temperature_summary.csv.
⬜ | Plot temperature trends alongside RH if desired. | Overlay plots for quick visual inspection.
Other Environmental Data (Wind)
Status | Task | Action
⬜ | Extract wind speed and direction from the DAQ weather‑station files. | Use the path MH DAQ\weather_station\2026.
⬜ | Compute average and standard deviation for the 2‑hour post‑shower window (and optionally the pre‑shower period). | Write to wind_summary.csv.
⬜ | For direction, apply circular statistics (e.g., scipy.stats.circmean). | Include a polar plot if helpful.
Results Consolidation & Reporting
Status | Task | Action
⬜ | Create a master Excel workbook (results_master.xlsx) with separate sheets for CO₂ λ, particle deposition/emission, RH, temperature, and wind. | Use pandas.ExcelWriter.
⬜ | Produce publication‑ready figures (time‑series, decay curves, RH/temperature trends, wind rose). | Follow style guidelines in the project (e.g., use bokeh for interactivity if needed).
⬜ | Write a concise final report (report.pdf) that: • Summarizes methodology (including the numerical “purple” equations). • Presents all key statistics and uncertainties. • Discusses any data‑quality issues. | Template can be based on the existing Data Analysis.docx outline.